## smartline
| id | title | status | assignee | labels | priority | estimate | start_date | end_date | closed_at
0 | 97 | Integrate usecases to UI | In Progress | NycollasSobolevski |  | P0
1 | 50 | Modal Component | Done | BecaIanz | Ui |  |  | 2025-08-01 | 2025-08-05 | 2025-08-13 18:08
2 | 10 | Cells | Waiting | NycollasSobolevski | Ui | P0
3 | 43 | Type of Input | Waiting | BecaIanz
4 | 36 | Validação Models | Waiting | trevisharp | Backend |  |  | 2025-07-24 | 2025-07-25
5 | 124 | FIX cell title on cell page | Waiting | NycollasSobolevski | Ui
6 | 1 | Home | Waiting |  | Ui | P1 | 0
7 | 14 | Database Model | Done | NycollasSobolevski | Database | P0 | 1 | 2025-07-09 | 2025-07-11 | 2025-07-14 11:41
8 | 109 | GetCells integration | Done | NycollasSobolevski | [5 empty] | 2025-09-09 18:25
9 | 7 | Daily | Done | NycollasSobolevski | Ui |  |  |  |  | 2025-08-27 17:32
10 | 26 | Check Box Group | Done | BecaIanz | [5 empty] | 2025-07-29 16:52
11 | 5 | All Products Page | Done | Heloise18 | Ui |  |  |  |  | 2025-08-05 17:52
12 | 40 | Input Component | Done | NycollasSobolevski | [5 empty] | 2025-07-29 16:52
13 | 35 | NewButton | Done | Heloise18 | Ui |  |  |  |  | 2025-07-28 13:23
14 | 13 | Change to Entity Framework | Done | CrCardd | Backend | P0 | 2 | 2025-07-14 | 2025-07-18 | 2025-07-18 16:49
15 | 2 | Products | Done |  | Ui | P1 |  |  |  | 2025-09-17 13:37
16 | 6 | Wastes | Done | NycollasSobolevski |  | P1 |  |  |  | 2025-09-11 19:57
17 | 99 | ClearWastes integration | Done | NycollasSobolevski | [5 empty] | 2025-09-15 12:03
18 | 106 | EditWaste Integration | Done | [6 empty] | 2025-09-15 11:48
19 | 98 | AddWaste Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-11 20:02
20 | 118 | SaveCellDetail Integration | Done | [6 empty] | 2025-09-09 18:25
21 | 101 | Create Product Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-04 17:36
22 | 19 | Calculate Process | Done | BecaIanz | Ui |  |  |  |  | 2025-08-28 17:52
23 | 4 | Edit Product | Done | BecaIanz | Ui |  |  |  |  | 2025-08-28 17:52
24 | 11 | Cell Component | Done | NycollasSobolevski | Ui | P1 | 2 | 2025-07-22 | 2025-07-16 | 2025-07-29 11:51
25 | 103 | EditProduct integration | Done | NycollasSobolevski | [5 empty] | 2025-09-04 17:36
26 | 59 | Edit Product | Done | [6 empty] | 2025-08-21 17:34
27 | 3 | Create Product | Done |  | Ui |  |  |  |  | 2025-09-17 13:36
28 | 12 | Edit Cell | Done | NycollasSobolevski | Ui |  |  |  |  | 2025-09-17 13:37
29 | 15 | Demand | Done |  | Ui | P1 |  |  |  | 2025-09-17 13:36
30 | 22 | Button Component | Done | Heloise18 | Ui | P2 |  |  |  | 2025-07-24 16:37
31 | 9 | Edit Waste | Done |  | Ui |  |  |  |  | 2025-09-11 19:57
32 | 8 | New Waste Component | Done | NycollasSobolevski | Ui |  |  |  |  | 2025-09-11 19:57
33 | 119 | Update Holiday integration | Done | [6 empty] | 2025-09-11 19:57
34 | 23 | Table component | Done | trevisharp | Ui |  |  |  |  | 2025-07-24 16:37
35 | 18 | Calendar (Current Procces) | Done | Heloise18 | Ui | P1 |  |  |  | 2025-09-16 16:29
36 | 38 | Dropdown component | Done | Heloise18 | [5 empty] | 2025-08-01 13:23
37 | 46 | Define UseCases | Done | trevisharp | Backlog |  |  |  |  | 2025-07-30 18:30
38 | 53 | Implementing UseCases | Todo | trevisharp | Backend
39 | 54 | Add Wastes Use Cases | Done | [6 empty] | 2025-08-05 13:52
40 | 78 | Component Period Range Selector | Done | Heloise18 | [5 empty] | 2025-08-18 19:35
41 | 55 | Create Wastes | Done | [6 empty] | 2025-08-05 13:52
42 | 56 | Create Demand | Done | [6 empty] | 2025-08-21 17:34
43 | 57 | Create Product | Done | [6 empty] | 2025-08-05 13:52
44 | 58 | Edit Demand | Done | [6 empty] | 2025-08-05 13:52
45 | 60 | Edit Setup | Done | [6 empty] | 2025-08-12 12:25
46 | 61 | Edit Waste | Done | [6 empty] | 2025-08-21 17:34
47 | 62 | Generate Calendar | Não planejado ainda
48 | 63 | Get Cell Detail | Done | [6 empty] | 2025-08-21 17:34
49 | 64 | Get Demand | Done | [6 empty] | 2025-08-21 17:34
50 | 65 | Get Product | Done | [6 empty] | 2025-08-21 17:34
51 | 66 | Get Waste Calendar | Done | [6 empty] | 2025-08-21 17:34
52 | 67 | Get Products | Done | [6 empty] | 2025-08-21 17:34
53 | 68 | Get Production Calendar | Done | [6 empty] | 2025-08-21 17:34
54 | 69 | Get Waste Calendar | Done | [6 empty] | 2025-08-21 17:34
55 | 70 | Get Waste Date Datail | Done | [6 empty] | 2025-08-21 17:34
56 | 71 | Get Waste Types | Done | [6 empty] | 2025-08-05 13:52
57 | 72 | Save Cell Details | Done | [6 empty] | 2025-08-21 17:34
58 | 73 | Update Holiday | Done | [6 empty] | 2025-08-21 17:34
59 | 88 | Fix wastes and Get Waste Details | Done | trevisharp | [5 empty] | 2025-08-26 12:54
60 | 95 | fix cells details | Done | NycollasSobolevski |  |  | 2 | 2025-08-28 | 2025-09-01 | 2025-08-29 17:08
61 | 100 | Create Demand Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-10 13:01
62 | 102 | Edit demand integration | Done | NycollasSobolevski | [5 empty] | 2025-09-10 12:55
63 | 104 | EditSetup Integration | Não planejado ainda
64 | 105 | EditWaste Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-15 12:06
65 | 107 | GenerateCalendar Integration | Não planejado ainda
66 | 108 | GetCellDetail Integration | Done | [6 empty] | 2025-09-10 13:01
67 | 110 | getCellsNames Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-15 12:07
68 | 111 | GetDemands integration | Done | NycollasSobolevski | [5 empty] | 2025-09-10 12:53
69 | 112 | GetProductDetail integration | Done | [6 empty] | 2025-09-10 12:58
70 | 114 | GetProducts Integration | Done | [6 empty] | 2025-09-10 13:02
71 | 115 | GetWasteCalendar Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-15 12:07
72 | 116 | GetWasteDateDetail Integration | Não planejado ainda
73 | 117 | GetWasteTypes Integration | Done | NycollasSobolevski | [5 empty] | 2025-09-15 12:08
74 | 126 | FIX getting disabled entities on join | Todo | trevisharp
75 | 130 | Calendar Page | In Progress | CrCardd | Backend | P0
76 | 113 | GetProductionCalendar integration | In Progress | Heloise18 | Integration | P1 |  | 2025-09-25
77 | 131 | Integrations | Todo | NycollasSobolevski | Test | P1 | 2 | 2025-10-06 | 2025-10-07
78 | 132 | Old results comparations | Todo | NycollasSobolevski | Test | P1 | 3 | 2025-10-08 | 2025-10-10
79 | 133 | User comparation (with client) | Todo | NycollasSobolevski | Test | P1
80 | 134 | SaveChangesCalendar Usecase | Não planejado ainda | Heloise18